## Gantt Chart
Investigate inter-layer delamination strength in fused deposition modelling (3D Printing)
Durham University
Adam Feaster | Dr Qing Wang
Project start date: | 2023-10-03 | [9 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May
|  |  |  | 2023-10-03 | 2023-10-10 | 2023-10-17 | 2023-10-24 | 2023-10-31 | 2023-11-07 | 2023-11-14 | 2023-11-21 | 2023-11-28 | 2023-12-05 | 2023-12-12 | 2023-12-19 | 2023-12-26 | 2024-01-02 | 2024-01-09 | 2024-01-16 | 2024-01-23 | 2024-01-30 | 2024-02-06 | 2024-02-13 | 2024-02-20 | 2024-02-27 | 2024-03-05 | 2024-03-12 | 2024-03-19 | 2024-03-26 | 2024-04-02 | 2024-04-09 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-05-07 | 2024-05-14 | 2024-05-21 | 2024-05-28
Milestone description | Progress | Start | Days | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue | Tue
Initial development
Research Academic Papers | 60% | 2023-10-01 | 40
Produce Initial Risk Assessment | 100% | 2023-10-10 | 9
Draft Initial Project Plan | 100% | 2023-10-10 | 20
Complete Test Prints - Find best printer settings and strut angles | 10% | 2023-10-23 | 25
Design Lattices on SOLIDWORKS - Non-Stotchastic and Free Form | 5% | 2023-10-23 | 25
Produce Mathematical Hypotheses Regarding the Lattices | 0% | 2023-11-06 | 24
Production and Testing
Produce Literature Review | 0% | 2023-11-23 | 61
Manufacture Lattices on Ender3 | 0% | 2023-11-13 | 75
Manufacture Lattices on Bambu | 0% | 2023-11-13 | 75
Anneal Half of the Lattices | 0% | 2024-01-06 | 25
Complete Compressive Tests | 0% | 2024-01-22 | 35
Complete Fatigue Life Analysis Tests | 0% | 2024-01-22 | 35
Complete 3-Point Bending Tests | 0% | 2024-01-22 | 35
Print Free-Form Lattice Structures | 0% | 2024-01-29 | 30
Submit Project Outline Report | 0% | 2024-01-20 | 40
Anneal Half of the Free-Form Lattices | 0% | 2024-02-12 | 30
Complete the three Tests for the New Structures | 0% | 2024-02-20 | 30
Results & Follow Up Work
Complete FEA if Required | 0%
Produce Final Report (22nd April) | 0% | 2024-03-10 | 40